## Sheet1
Task | Note
Catalog Content | Is there any reason we can't simply use the Wiki's table of contents?
Identify Authors | Authorship is also documented within the Wiki. Is this enough?
Contact Authors | Let the authors know the plan and give them options (sunset the content, migrate the content, freeze the content
Gather and assess Author feedback | Based on the feedback we can scope the remainder of the project
Lock Wiki from additional updates
Identify migration destination
Formalize migration process | One author at a time? Manual migration, scripted etc?
Provide authors with hard cutover dates
Announce plan to all Commons | Prepare announcements for consumers of content that there content may be moving or going away
Remove all "sunsetting content" | Follow published dates
Migrate all "migrating content" | Follow published dates
Ask authors to verify complete migration
Shut down Wiki | Archive content